## Slide 1: WP Monitoring & Services
NectarCAM F2F Meeting, 10-12 October 2022

## Slide 2: WP Monitoring & Services: Agenda
Power Supply Box (PSB)
Power Distribution Box (PDB)
Embedded Camera Controller (ECC)
Progress status
Production
CDMR RIX status
Fred Louis (IRFU)
Julie Prast (LAPP)

## Slide 3: EMBEDDED CAMERA CONTROLLER
Julie Prast for the LAPP team
NectarCAM F2F, 10-12 October 2022

## Slide 4: ECC Status
Common component between NectarCAM and LSTCAM
  Same hardware
  Same software with dedicated camera configuration
Status
  LST2-4 cabinets + LST engineering model cabinet were delivered in 2021
  LSTCAM1 ECC has been upgraded in September 2022
  Old LSTCAM1 ECC will be upgraded to become the LST spare
  NectarCAM Adlershöf cabinet has been upgraded early 2022
    Includes new NectarCAM mechanics with mounting on rails to ease cabinet replacement
    Currently used in NectarCAM1
  One additional NectarCAM cabinet includes the same electronic, same software, but first version of mechanics
    Used for the NectarCAM testbench (Tower 66)
All these 8 ECC have the same electronics and the same software
  The white target control has been removed (IJClab responsibility in NectarCAM)
  Any software upgrade (bug correction…) on one side is immediately reverberated on the other camera

## Slide 5: Production Hardware
Optimization of the ECC cabinet for manufacturing
Development of an Interface Board to replace most of the internal cables
White Target control removed
Old LST1 (left) versus new LST1 ECC (right) on the LST access tower

## Slide 6: NectarCAM Production
9 cabinets have to be produced (NectarCAM 2-9 +1 spare)
A call for tender has been issued in July
  5 + 4 cabinets
  4 companies made an offer. Comparison is to be done
The call for tender includes
  Mechanical cabinet manufacturing (based on Oscar Ferreira’s drawings)
  Purchase of small components and cables
  Cabinet cabling
  First level tests
The call for tender does not include
  The National Instrument components purchase (long delivery time, ordered in advance)
  The functional verification
  The manufacturing of electronics boards (LEDs and Interface Board) which were already produced
Interface Board
LED Controller

## Slide 7: NectarCAM Production (2)
Price is in the order of amount of what was expected
  NI components ordered for 5 ECC in December 2021
  NI components ordered for 4 ECC in July 2022: ~ + 50% compared to December 2021 !
Delay is in the order of 6 months to receive the 5 first units
  The longest is the manufacturing of the mechanical crate
  NI components for the 9 units are available
  Delay for the 4 additional cabinets is ~5 months
The production can start as soon as the company is selected

## Slide 8: ECC Test and Quality Control
ECC test procedures have been written
  MST-CAM-TP-0421-LAPP_ECC_Test_Plan
ECC test result sheet templates are available
  LMST-CAM-TR-0422-LAPP_ECC_OPCUA_Method_Test Results_Template
  LMST-CAM-TR-0423-LAPP_ECC Test Results_Template
NectarCAM1 production cabinet was delivered with the associated Acceptance Delivery Package thanks to our local quality engineer (she has left since)
Production test is foreseen with the current testbench equipped with camera sensors & actuators
If it is ready on time a dedicated testbench will be used
  It is based on a compact RIO and dedicated I/O modules to simulate camera sensors/actuators
  Emulated from OPCUA interfaces
  Errors can be generated
  Transportable on site thanks to a plane cabin suitcase format

## Slide 9: Transportable Testbench
Hardware developed by the student Maxime Boute in S1 2022
Software development ongoing (Nadia)
ECC
Suitcase
LabVIEW test program
Injection, monitoring, comparaison
Simulation of PT100 + 5V Fan tachymeters

## Slide 10: Monitoring & Control WP RIX Status
39 Monitoring & Control RIXes were issued
  Includes ECC, PSB and PDB matters
  36 normal priority + 3 low priority
  35 are closed
  4 are not closed but assigned to CTAO (2 NW, 1 OS, 1GP)
Zero non-closed RIX are still assigned to NectarCAM

## Slide 12: Finalization of Production Software
Completely new version of code
  Based on current validated ECC features
  New architecture, more compact and better structured
  Integrates most of the various review recommendations (CTA, LST, NectarCAM, IN2P3, …)
  Based on LabVIEW 2018
Additional features:
  State machine transitions improved
  Alarm handling & identification improved
  Additional monitoring info (ongoing methods, CPU load, ECC versions, debug…)
  Additional parameters accessible in the configuration file
  Updated chiller & shutter interfaces
  Additional sensor & actuator interfaces
Feb 2020: First release installed at IRFU
Feb 2021 : release of ECC Software V5.0